## Feuil1
Date | Project phase | Module | Work content | Working hours | Overtime | Comments
2012-11-04 | Requirement Analysis | Personnel division | Work division, preliminary completion of requirement understanding list document, creation of a svn server | 3 hours, from 2pm to 5pm | 1 hour | Solvation of problems with GitServer installation
2012-11-05 | Requirement Analysis | Personnel division | Continuing work division and completion of requirement understanding list document by each members. Meeting hold. | 6 hours, from 8am to 11:30am, from 2pm to 5pm |  | Deliverables sent : Project Grouping Document, Daily Report Document, Requirement Understanding List Document, GitHub adress